## Sheet1
Mandatory/ Optional | Functionality | Test Case | Expected Result | Actual Result | Status | Screenshot Reference
Mandatory | Create ABHA Option | The system must provide an option to create ABHA through Aadhaar OTP | User will have an option to create ABHA | The “Create ABHA” option was clearly visible on the screen. | ✅ Pass | Create ABHA Option.PNG
|  | The system must redirects to Aadhaar entry screen after selecting “Create ABHA Account" | Upon selection, the system should open the Aadhaar entry page for user input | The system redirected the user correctly to the Aadhaar entry screen | ✅ Pass | Aadhar No Screen.PNG
Mandatory | Consent collection | The system must display the consent language/ disclaimer language and collect user's consent as per the ABDM published consent. | User provides consent for sharing of Aadhaar details and creation of ABHA. System records user consent for compliance with Health Data Management Policy. | The system does not display the declaration statement “I hereby declare that” at the header of the consent language section.The consent language should begin with “I hereby declare that” as per the approved consent format. | ❌ Fail | Consent Message Error.PNG
| Aadhaar collection and Error Message | 1. The system must accepts a valid 12-digit Aadhaar number | System should accept the 12-digit Aadhaar number and proceed to OTP | System accepted the valid Aadhaar number and displayed OTP verification screen | ✅ Pass | Valid 12 digit Aadhar No.PNG
Mandatory |  | 2. The system displays a proper error message for an invalid Aadhaar number format | User is prompted to enter correct Aadhaar Number In case user enters an invalid Aadhaar number (A valid Aadhaar is a 12-digit number), the system shows an error message "Aadhaar Number is not valid". | 1. The system displays the error message “Aadhaar must be 12 digits” instead of the standard message "A valid Aadhaar is a 12-digit number". 2. The system displays the error message “Invalid Aadhaar Number” instead of the standard message "Aadhaar Number is not valid". Update the error text to A valid Aadhaar is a 12-digit number and "Aadhaar Number is not valid" . | ❌ Fail | Aadhar Collection Error Message.PNG
| Aadhaar OTP Collection | User receives Aadhaar OTP and System must allow the user to enter Aadhaar OTP. | The system should allow the user to input the received OTP digits in the provided field | System allowed user to enter the OTP | ✅ Pass | Aadhar OTP.PNG
Mandatory |  | The system should displays a message indicating that the OTP has been sent | System should display message "Please enter 6 -digit OTP sent to Aadhaar linked mobile number " step during the ABHA Creation workflow with “We just sent an OTP on the Mobile Number *******XXXX linked with Aadhaar. Enter the OTP below to proceed with ABHA creation". | The system did not display the masked mobile number message after sending the OTP. User was redirected directly to the OTP entry screen without showing the message | ❌ Fail | Aadhar OTP Collection Error Message.PNG
Mandatory | Resend OTP | The system allows resending OTP when the first OTP expires | User will able to send OTP again and verify it | The “Resend OTP” functionality is not yet developed in the system. The option is missing from the OTP verification screen. | ❌ Fail
Mandatory | Communication Mobile Number verification-II | If communication mobile number is not same as Aadhaar linked mobile number then system must ask for the OTP to verify comuncation mobile number. | System verifies the communication mobile number | The “Communication Mobile Number verification-II” functionality is not yet developed in the system. The option is missing from the verification screen. | ❌ Fail
| ABHA Address | The system allows creating multiple ABHA addresses for a single ABHA number | The system should allow a user to create and manage multiple ABHA addresses (e.g., user@sbx, user1@sbx) linked to the same ABHA number as per ABDM functionality. | In the existing system, there is no option available to create multiple ABHA addresses for a single ABHA number. The interface supports only one ABHA address per ABHA number. | ❌ Fail | Multiple ABHA Address.PNG
| HIMS Integration | The system links ABHA number with HIMS system after successful ABHA creation | After ABHA creation, the system should automatically link the created ABHA number with the HIMS system without error. | In the existing system, there is no functionality available for linking ABHA data with the HIMS system. After ABHA creation, the system crashes instead of proceeding with linkage | ❌ Fail | HIMS Crash.PNG